# Riverside Renovation
Project Status Report

Overall status: On track | Reporting period: July 2026

Overview

Interior demolition is complete, structural repairs are 80% finished, and framing is progressing to plan. A critical coordination review for mechanical, electrical, and plumbing interfaces is scheduled before rough-in begins.

Risks

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Hidden utility conflicts | High | Complete critical subsurface verification before floor penetrations and reserve a response allowance. |
| Long-lead fixture delays | Medium | Confirm supplier dates weekly and pre-approve equivalent fixtures. |
| Tenant access disruption | Medium | Sequence noisy work outside peak hours and maintain a clearly marked alternate route. |
| Weather delays | Medium | Add weather contingency days and resequence exterior work when forecasts show unsafe conditions. |

Next Steps

Complete the MEP coordination review, close open structural punch items, release the rough-in work packages, and issue the two-week look-ahead schedule.